## Program 2026
Project Status | Initiative Name | Project Name | Description | DT Team Accountable | OTD Status | State | Phase | Estd. Start Date | Estd. End Date | Adjusted End Date | Category | Business Unit | Primary Function | Region | Executive Sponsor | 2026 budget? | 2026 Benefits Plan | DT Team Accountable | DT Teams Involved | For Filter Purposes | DT lead | Business Project Lead | Level of Effort | Technology | Budget
G | M&A - PERS realignment to Gas Power | PERS to Gas Power Controls | Business Development Activity | Technology Enablement & Transformation | On Track | Active | Discovery |  | 2025-01-26 |  | MustDo | PERS | All |  |  | N | N | Technology Enablement & Transformation | All | Technology Enablement & TransformationAll | Taufan Tjioe
G | Hardware and Platform Obsolesence | Hardware and Platform Obsolesence - Edinburgh | Replacement of legacy platform in the Edinburgh datacenter to reduce hardware failure risk and cyber obsolesence. | Product Tech Solutions & Operations | On Track | Active | Launch |  | 2026-03-30 |  | MustDo | Grid | DT |  | Ross McIntyre | Y | Y | Product Tech Solutions & Operations | Grid DT Ops | Product Tech Solutions & OperationsGrid DT Ops | Steven Smith | N/A
G | M&A Project Montreal (NDA) | Project Montreal (NDA) | NDA Business Development Activity | Technology Enablement & Transformation | On Track | Active | Requirements | 2025-02-01 | 2026-04-01 |  | Strategic/LTGrowth | All | M&A | Global | Geoffrey Marsh | Y | N/A | Technology Enablement & Transformation | Data & Analytics | Technology Enablement & TransformationData & Analytics | Taufan Tjioe | Russama Niramolsophakul | Large
G | ERP DevOps | IACS Large table partitioning | Finance maintenance of indexing X large table with Golden Gate | Enterprise Applications | On Track | Closure | Post-Launch |  | 2026-04-01 |  | MustDo | All | Finance |  | Reema Nath | N | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Seshu Kilaru | Seshu Kilaru
G | Grid ServiceNow Transformation | Grid Customer Portal | Customer portal for Grid on ServiceNow | Enterprise Applications | On Track | Active | Post-Launch |  | 2026-05-31 |  | Strategic/LTGrowth | Grid | Customer Success | Global | Vince Padua | Y | Y | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Catherine Lee, Abhishek Ramachandran | Tucker King | XLarge
G | Vernova HQ Initiatives | HR3 integration failures | HR3 integration failures because IFG has changed to GE Renewable Energy from GE Digital | Enterprise Applications | On Track | Active | Build |  | 2026-06-01 |  | MustDo | All | All | Global |  | Y | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Seshu Kilaru | NA | Medium
G | Vernova HQ Initiatives | TC exit | Move all Thread Connect integration to OIC | Enterprise Applications | On Track | Closure | Post-Launch |  | 2026-06-01 |  | MustDo | All | All | Global | Sripati Neti | Y | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Kishore Pasumarty | NA | Medium
G | Vernova HQ Initiatives | Benin LE migration | Benin LE migration to Fusion | Data & AI | Adjusted plan | Active | Verify |  | 2026-05-01 | 2026-07-25 | MustDo | Grid | Finance |  | Tom Mabry | Y | N/A | Digitization Programs | Digitization Programs | Digitization ProgramsDigitization Programs | Bala Chander | Segun Akinsanya
G | Grid A&S Pipeline Reporting | Grid CRMA Integration | Grid CRMA Integration | Enterprise Applications | On Track | Active | Build |  | 2026-07-01 |  | MustDo | All | All | Global | Brenna Burns | Y | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | David Cox | NA | Medium
G | Vernova HQ Initiatives | GE Rebranding | Migrate all UX, Email and Domain to GE Vernova branding | Enterprise Applications | On Track | Active | Build |  | 2026-07-01 |  | MustDo | All | All | Global | James Kiger | Y | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Mahesh Acholkar | James Kiger
G | M&A Project Eagle - Alteia | Project Eagle (NDA) | NDA Business Development Activity | Technology Enablement & Transformation | On Track | Active | Build | 2025-12-01 | 2026-07-01 |  | Strategic/LTGrowth | Grid | M&A | EMEA | Brian Hoff | Y | N/A | Technology Enablement & Transformation | Data & Analytics | Technology Enablement & TransformationData & Analytics | Taufan Tjioe | Taufan Tjioe | Large
G | Unit Economics | Discovery - MS Access DB | Fit/Gap; Process Maps; Existing systems | Data & AI | On Track | Active | Discovery |  | 2026-07-26 |  | Productivity | Grid | Finance |  | Raman Nagarajan | Y |  | Data & Analytics |  | Data & Analytics | Emily Schreiner/Charles Norton |  | Large
G | Unit Economics | Discovery - Product Workstream | Fit/Gap; Process Maps; Existing systems | Data & AI | On Track | Active | Discovery |  | 2026-07-26 |  | Productivity | Grid | Finance |  | Raman Nagarajan | Y |  |  |  |  | Emily Schreiner |  | Small
G | Unit Economics | Discovery - Cash Workstream | Fit/Gap; Process Maps; Existing systems | Data & AI | On Track | Active | Discovery |  | 2026-07-26 |  | Productivity | Grid | Finance |  | Raman Nagarajan | Y |  |  |  |  | Emily Schreiner |  | Medium
G | Unit Economics | Discovery - Services Workstream | Fit/Gap; Process Maps; Existing systems | Data & AI | On Track | Active | Discovery |  | 2026-07-26 |  | Productivity | Grid | Finance |  | Raman Nagarajan | Y |  |  |  |  | Emily Schreiner |  | Medium
G | Unit Economics | Discovery - Support Workstream | Fit/Gap; Process Maps; Existing systems | Data & AI | On Track | Active | Discovery |  | 2026-07-26 |  | Productivity | Grid | Finance |  | Raman Nagarajan | Y |  |  |  |  | Emily Schreiner |  | Medium
G | Unit Economics | Discovery - Profitability Workstream | Fit/Gap; Process Maps; Existing systems | Data & AI | On Track | Active | Discovery |  | 2026-07-26 |  | Productivity | Grid | Finance |  | Raman Nagarajan | Y |  |  |  |  | Emily Schreiner |  | Small
| Vernova HQ Initiatives | GEV HQ Initiative to update all Divisions | GEV HQ Initiative to update all Divisions (IFG, Segment, Sub-Business) in WD / Atlas / Fusion | Enterprise Applications | On Track | Active | Discovery |  | 2026-08-01 |  | MustDo | All | All | Global |  | Y | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Seshu Kilaru |  | Large
G | Hardware and Platform Obsolesence | Hardware and Platform Obsolesence - Lynnwood | Replacement of legacy platform in the Edinburgh datacenter to reduce hardware failure risk and cyber obsolesence. | Product Tech Solutions & Operations | Slip | Active | Build |  | 2026-03-30 | 2026-08-26 | MustDo | Grid | DT |  | Ross McIntyre | Y | Y | Product Tech Solutions & Operations | Grid DT Ops | Product Tech Solutions & OperationsGrid DT Ops | Steven Smith | N/A
G | Vernova HQ Initiatives | MJE Approval alignment | MJE Approval process to align with GEV HQ Process | Data & AI | Adjusted plan | Active | Requirements |  | 2026-05-01 | 2026-09-26 | MustDo | All | Finance |  | Tricia Elgee | N | N/A | Digitization Programs | Digitization Programs | Digitization ProgramsDigitization Programs | Bala Chander | Tricia Elgee
| Tableau to Power BI Migration | Tableau to Power Migration | Migrate Tableau dashboards to Power BI to save $100K/year in costs | Data & AI | On Track | Active | Build |  | 2026-10-26 |  | MustDo |  | All |  | Raman Nagarajan | Y | Y |  |  |  | Emily Schreiner
| Grid ServiceNow Transformation | Grid Customer Portal Pro+ enablement | Enable advanced AI and agentic capabilities on ServiceNow | Enterprise Applications | On Track | Active | Discovery |  | 2026-12-31 |  | Strategic/LTGrowth | Grid | Customer Success | Global | Vince Padua | Y | Y | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Reza Rahman | Tucker King | XLarge
Y | Vernova HQ Initiatives | OneIDM exit to MAP | Migrate OneIDM to My Access Portal (MAP) | Enterprise Applications | Adjusted plan | Active | Build |  | 2026-12-01 |  | MustDo | All | All |  | Sripati Neti | N | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Seshu Kilaru | Sripati Neti
G | L2C Transformation | Grid AI enabled Proposal Management (Phase 1) | AI Enabled peoposal management tool to generate proposals from DD0-DD3 steps | Enterprise Applications | On Track | Active | Build | 2025-10-01 | 2027-07-01 |  | Productivity | Grid | Commercial | Global | Brenna Burns | N/A | Y | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Reza Rahman | Praveen Lala | Extra Large | SFDC, Oracle CPQ, Proporal Mgmt. Platform
G | DevOps | Data Operations - Defect Support | Placeholder for Data DevOps work | Data & AI | On Track | Active | Build |  | 2026-12-26 |  | MustDo |  | All |  | Reema Nath | Y |  |  |  |  | Emily Schreiner | Many | Small
G | Data Enhancements | Data Operations - Enhancements | Placeholder for small enhancements executed by the Data Run Team | Data & AI | On Track | Active | Build |  | 2026-12-26 |  | Productivity |  | All |  | Reema Nath | Y |  |  |  |  | Emily Schreiner | Many | Medium
G | Alteia migration | Alteia S2P migration to Fusion | Alteia S2P migration to Fusion - Procure to Pay | Data & AI | On Track | Active | Discovery |  | 2027-05-01 |  | Strategic/LTGrowth | Grid | Finance |  | Raman Nagarajan, Elena Bachniak | Y | N | Digitization Programs | Digitization Programs | Digitization ProgramsDigitization Programs | Bala Chander | Elena Bachniak
G | L2C Transformation | Grid Q2C transformation + Alteia Q2C Migration | Grid Q2C transformation + Alteia Migration | Enterprise Applications | Adjusted plan | Active | Discovery | 2025-05-01 | 2027-06-01 |  | Strategic/LTGrowth | Grid | Commercial | Global | Raman Nagarajan, Praveen Lala | Y | N | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Reza Rahman | Praveen Lala | Extra Large | Oracle CPQ, SFDC, OIC, Fusion
| Vernova HQ Initiatives | Corp ITO Project Tracking | Corp ITO Project Tracking | Enterprise Applications | On Track | Active | Discovery |  |  |  | MustDo | All | All | Global | Sonna Brown | Y | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | David Cox | NA | TBD
| Vernova HQ Initiatives | Corp Compliance Hub |  | Enterprise Applications | On Track | Active | Discovery |  |  |  | MustDo | All | All | Global |  | Y | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | David Cox | NA | TBD
| ERP Infrastructure | IACS Retirement | Retire IACS and continue to send data to VDL | Data & AI |  | Evaluation | Requirements |  |  |  | MustDo |  | Finance |  | Raman Nagarajan | [5 empty] | Minal Merchant |  | XLarge
| Data & AI Platform | Data & AI Platform Discovery | Evaluation and Recommendation of Data & AI platform | Data & AI |  | Evaluation | Requirements |  |  |  | Strategic/LTGrowth | Grid | All | Global | Raman Nagarajan | N |  |  |  |  | Minal Merchant |  | XLarge
| GitHub.com | GitHub.com | Grid SW move from GitHub Entprise Server to SaaS GitHub.com | Product Tech Solutions & Operations |  | Evaluation | Requirements |  |  |  | Strategic/LTGrowth | Grid | Engineering | Global | Jagan Rahgu | N |  | Technology Enablement & Transformation | Technology Enablement & Transformation | Technology Enablement & TransformationTechnology Enablement & Transformation | Steven Smith | Jagan Raghu | Large
|  | ESW Software Investment and Governance Framework | Implement a system that allows for centralized management of software licenses, agreements, contracts and costs across all of ESW. | Technology Enablement & Transformation |  | Evaluation | Requirements |  |  |  | Productivity | All | DT | Global | Prakash Seshadri |  |  | Technology Enablement & Transformation |  | Technology Enablement & Transformation
| Alteia migration | Alteia S2P migration to Fusion | Alteia S2P migration to Fusion | Data & AI |  | Funnel | [11 empty] | Digitization Programs | Digitization Programs | Digitization ProgramsDigitization Programs | Bala Chander
| Alteia migration | Odoo Retirement |  | Data & AI |  | Funnel
| Data & AI Platform | Data & AI Platform Implementation | Implementation of Data & AI platform | Data & AI |  | Funnel |  |  |  |  | Strategic/LTGrowth | Grid | All | Global | Raman Nagarajan | N |  | Data & Analytics |  | Data & Analytics | Minal Merchant
| ERP Enhancements | Enable AI in Fusion ERP |  | Data & AI |  | Funnel | [11 empty] | Digitization Programs | Digitization Programs | Digitization ProgramsDigitization Programs | Bala Chander
| ERP Enhancements | Oracle Fusion Enhancements (Finance, Services) |  | Data & AI |  | Funnel | [9 empty] | N
| ERP Enhancements | Enable Timesheet in P6 & integration to Fusion |  | Data & AI |  | Funnel
| M&A - PERS realignment to Gas Power | ERP Data Migration |  | Data & AI |  | Funnel
| Unit Economics | Unit Economics Intermediate Automation - MS Access DB | Automating existing process | Data & AI |  | Funnel | [9 empty] | N
| Unit Economics | Unit Economics Intermediate Automation - Product Workstream | Automating existing process | Data & AI |  | Funnel
| Unit Economics | Unit Economics Intermediate Automation - Cash Workstream | Automating existing process | Data & AI |  | Funnel
| Unit Economics | Unit Economics Intermediate Automation - Services | Automating existing process | Data & AI |  | Funnel
| Unit Economics | Unit Economics Intermediate Automation - Support | Automating existing process | Data & AI |  | Funnel
| Unit Economics | Unit Economics Intermediate Automation - Profitability | Automating existing process | Data & AI |  | Funnel
| Unit Economics | System of Record - MS Access DB | Fully automated from systems of record (not Excel) | Data & AI |  | Funnel | [9 empty] | N
| Unit Economics | System of Record - Profitability | Fully automated from systems of record (not Excel) | Data & AI |  | Funnel
| Unit Economics | System of Record - Support | Fully automated from systems of record (not Excel) | Data & AI |  | Funnel
| Unit Economics | System of Record - Services | Fully automated from systems of record (not Excel) | Data & AI |  | Funnel
| Unit Economics | System of Record - Product | Fully automated from systems of record (not Excel) | Data & AI |  | Funnel
| Unit Economics | System of Record - Cash | Fully automated from systems of record (not Excel) | Data & AI |  | Funnel
| Vernova HQ Initiatives | Ledger Based Reporting (Phase 2) | Revamp CoCo and Natural Account, LE migration from SAP to Fusion | Data & AI |  | Funnel |  |  |  |  | Productivity | All | Finance | Global | Tricia Elgee |  |  | Digitization Programs | Bala Chander | Digitization ProgramsBala Chander | Bala Chander | Tom Welcome | Large
| Vernova HQ Initiatives | Migrate CCL Classic to CCL Fusion | GEV HQ | Data & AI |  | Funnel | [8 empty] | Tom Welcome/Tricia Elgee
|  | Engineering Flow Metrics |  | Data & AI |  | Funnel | Discovery
| ERP Enhancements | Oracle Fusion Enhancements which will be transitioned from Seshu to Mina;'s team |  | Data & AI |  | Funnel
| Grid ServiceNow Transformation | AI enablement of ServiceNow | Execute on the AI enablement roadmap for ServiceNow, using Customer Service Pro Plus capabilities | Enterprise Applications |  | Funnel | Funnel |  |  |  | Productivity | Grid | Commercial | Global | Tucker King | N | N | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Reza Rahman | Tucker King | Extra Large | ServiceNow
|  | VMR, VMO and Contract Management | Adopt a management system for DT vendor contracts to assist with renewals, budget allocation and portfolio | Technology Enablement & Transformation |  | Funnel | Requirements |  |  |  | Productivity | All | All |  | Reema Nath | N | N | Technology Enablement & Transformation | Technology Enablement & Transformation | Technology Enablement & TransformationTechnology Enablement & Transformation | Taufan Tjioe | TBD
|  | Slack for Grid Engineering and Alteia | Evaluate and securely implement the use of Slack for Grid Engineering Teams | Technology Enablement & Transformation |  | Funnel | Discovery |  |  |  | Productivity | Grid | Engineering |  | Brian Hoff | N | N | Technology Enablement & Transformation | Product Technology Solutions & Infrastructure | Technology Enablement & TransformationProduct Technology Solutions & Infrastructure | Taufan Tjioe | Devang Gandhi
|  | PC and Mac Image Validation | Develop scripts which run regression tests against common engineering use cases to validate that the latest PC and Mac images will work for software engineers | Product Tech Solutions & Operations |  | Funnel | Discovery |  |  |  | Productivity | All | Engineering | Global | Prakash Seshadri | N | N | Technology Enablement & Transformation | Technology Enablement & Transformation | Technology Enablement & TransformationTechnology Enablement & Transformation | Taufan Tjioe | Denny Walsh
| GrIp | GrIP Program | Grid Services Grip tool must undergo change prior to March 2027 | Product Tech Solutions & Operations |  | Funnel | Discovery | 2026-01-26 |  |  | Productivity | Grid | Engineering |  | Kapil Kapoor | N | N | Technology Enablement & Transformation |  | Technology Enablement & Transformation | Catherine Lee | Umesh Adlaka | Extra Large
| Grid Product360 | Phase 2 Discovery | Obtain stakeholder buy in for execution of expanding data model and adding AI capabilities | Data & AI |  | Hold | Discovery |  |  |  | Strategic/LTGrowth | Grid |  |  | Vince Padua | N |  | Data & Analytics |  | Data & Analytics
| OneLake Data Ingestion | VNDLY Contractor Data | VNDLY contractor data for analytics purposes | Data & AI |  | Hold | Discovery |  |  |  | Productivity |  | All |  | Becky Bach
| OneLake Data Ingestion | T&L Data | T&L data for analytics purposes | Data & AI |  | Hold | Discovery |  |  |  | Productivity |  | All |  | Becky Bach
| L2C Transformation | Grid CPQ | Roll out CPQ platform to Grid |  | On Track | Closure | Post-Launch | 2024-06-01 | 2025-07-30 |  | Strategic/LTGrowth | Grid | Commercial | Global | Praveen Lala | Y | Y | Enterprise Applications | SFDC & CPQ Team | Enterprise ApplicationsSFDC & CPQ Team | Avinash Udupa | Praveen Lala | Extra Large | SFDC, Oracle CPQ
|  | Consolidate ITCM into ServiceNow | Merge multiple IT Change Management tools into ServiceNow |  | On Track | Closure | Post-Launch |  | 2025-08-25 |  | Productivity | All | DT | Global | Cecil Mathew | Y |  | Digitization Programs |  | Digitization Programs | Seshu Kilaru | N/A | Small
| Keystone (formerly SSOT) | SSOT - Release 1 | KPI metrics (Commercial Pipeline, Orders, Revenue) |  | On Track | Closure | Post-Launch | 2025-01-01 | 2025-08-15 |  | Strategic/LTGrowth | All | Finance | Global | Jon Bosland | Y |  | Data & Analytics | Digitization Programs | Data & AnalyticsDigitization Programs | Emily | Palmer Hong | Large | EMR, Tableau
| L2C Transformation | ARR Wave 1 | LTC Transformation |  |  | Closure | Post-Launch |  |  |  | Strategic/LTGrowth | All | Comm&Mktg | Global | Prakash Seshadri | Y |  | Digitization Programs | Data & Analytics | Digitization ProgramsData & Analytics | Deepak Rohitas | Jeff Bartoletti | Large
| Keystone (formerly SSOT) | SSOT Kaizen | KPI metrics (Commercial Pipeline, Orders, Revenue) |  |  | Closure | Post-Launch |  |  |  | Productivity | All | DT | Global | Jon Bosland | Y |  | Digitization Programs |  | Digitization Programs | Bala Chander | Cecil Mathew | Medium
| DT Strategic Initiative | OIC Gen3 Upgrade | Upgrade the OIC platform and integrations from GEN 2 to GEN 3 |  | On Track | Closure | Post-Launch | 2024-06-01 | 2025-01-01 |  | MustDo | All | DT | Global | Kishore Pasumarty | Y | Y | Enterprise Applications | Kishore Pasumarty | Enterprise ApplicationsKishore Pasumarty | Kishore Pasumarty | Kishore Pasumarty | Large
| Grid Services Resourcing Initiative | Demand Planning Dashboard | Create automated reporting to help with resourcing decisions for the Grid Services team |  | On Track | Closure | Post-Launch | 2024-10-01 | 2025-08-20 |  | Strategic/LTGrowth | Grid | Customer Success | Global | Raman Nagarajan | Y |  | Data & Analytics |  | Data & Analytics | Emily | Molly Schwarzmiller | Large | EMR, Tableau
| Grid Services Resourcing Initiative | Deal Pipeline Dashboard | Created automated reporting to help the Grid team determine future resource needs |  | On Track | Closure | Post-Launch |  | 2025-08-01 |  | Strategic/LTGrowth | Grid | Customer Success | Global | Raman Nagarajan | Y |  | Data & Analytics |  | Data & Analytics
| Keystone (formerly SSOT) | SSOT - Release 2 | KPI metrics (Commercial Pipeline, Orders, Revenue) |  | On Track | Closure | Post-Launch |  | 2025-08-01 |  | Strategic/LTGrowth | All | Finance | Global | Jon Bosland | Y |  | Data & Analytics |  | Data & Analytics | Emily
| PMO Analytics | Engineering Bowler Dashboard | Digitize the Engineering Bowler for Prakash |  | Adjusted plan | Closure | Post-Launch | 2024-10-01 | 2025-08-31 | 2025-09-01 | Productivity | All | Engineering | Global | Prakash Seshadri | Y |  | Data & Analytics |  | Data & Analytics | Emily | Vinay Jammu | Large | EMR, Tableau
| PMO Analytics | Grid Headcount Dashboard | Digitize the recording and sharing of headcount allocation and forecasting |  | Adjusted plan | Closure | Post-Launch |  | 2025-08-01 | 2025-09-01 | Productivity | Grid | Engineering | Global | Prakash Seshadri | Y |  | Data & Analytics |  | Data & Analytics | Emily | Vinay Jammu
| PMO Analytics | GridOS Product360 Dashboard - Phase 1 | Provide a holistic view of the GridOS Program |  | On Track | Closure | Post-Launch |  | 2025-09-25 |  | Strategic/LTGrowth | Grid | Engineering | Global | Prakash Seshadri | Y |  | Data & Analytics |  | Data & Analytics | Emily | Lance Grow
| BD Project Sakura - TOP | Project Sakura - TOP | Employee to Contractor for legacy Grid |  | On Track | Closure | Post-Launch | 2024-10-01 | 2025-08-01 |  | Strategic/LTGrowth | Grid | M&A | Global | Rebecca Bach | Y | N/A | Technology Enablement & Transformation |  | Technology Enablement & Transformation | Taufan Tjioe | Steven Smith | Large
| M&A Project Slate - ROB-EX | Project Slate - ROB-EX | Acquisition DT Onboarding |  | On Track | Closure | Post-Launch |  | 2025-12-25 |  | Strategic/LTGrowth | Mfg | M&A | Global | Jakob Hall | Y | N/A | Technology Enablement & Transformation | Technology Enablement & Transformation | Technology Enablement & Transformation | Daniele Buttigli
| L2C Transformation | Lead-to-Cash Transformation Wave 2.2 | Wing-to-wing transformation of ITO and OTR |  | Adjusted plan | Closure | Post-Launch |  | 2025-11-01 | 2026-02-20 | Strategic/LTGrowth | All | Commercial | Global | Scott Reese | Y | N | Enterprise Applications | All | Enterprise ApplicationsAll | Reza Rahman | Jeff Bartoletti, Kelly Thomas & Melissa Eleuteri
| Marketing Transformation | Zoominfo Implementation | Improve the lead generation capabilities of the BUs |  | On Track | Closure | Post-Launch | 2025-03-01 | 2025-12-31 |  | Strategic/LTGrowth | All | Marketing | Global | Jeff Bartoletti, Tracy Dearing, Tracy Swartzendruber | Y | Y | Enterprise Applications | Brittany Lyons, Sharath Kumar | Enterprise ApplicationsBrittany Lyons, Sharath Kumar | Brittany Lyons | Bindu Oleti, Lauren Hewlett | Large | SFDC, 6Sense, Zoominfo, Marketo, Hive
| Vernova HQ Initiatives | GE Aerospace ThreadConnect Decommissioning | Migrating OneIDM ThreadConnect integrations to OIC |  | On Track | Closure | Post-Launch | 2025-01-01 | 2026-02-01 |  | MustDo | All | All | Global | Sripati Neti | N | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Kishore Pasumarty | Sripati Neti | Medium
| Vernova HQ Initiatives | Atomic replacement with Control-M | Migrate all Atomic jobs to Control-M as we are exiting the Broadcom contract |  | On Track | Closure | Post-Launch |  | 2026-01-01 | 2026-01-01 | MustDo | All | Finance |  | Christina Clark | N | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Seshu Kilaru | Matt Singer
| L2C Transformation | Lead-to-Cash Transformation Wave 2.3 | Wing-to-wing transformation of ITO and OTR |  | Adjusted plan | Closure | Post-Launch |  | 2026-02-01 | 2026-01-01 | Strategic/LTGrowth | All | Commercial | Global | Scott Reese | Y | Y | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Reza Rahman | Jeff Bartoletti, Kelly Thomas & Melissa Eleuteri
| L2C Transformation | Einstein Opportunity Scoring | AI enabled Opportunity & Lead scoring |  | Adjusted plan | Closure | Post-Launch |  | 2025-10-01 | 2026-03-01 | Strategic/LTGrowth | All | Commercial | Global | Reema Nath, Melissa Euleteri | Y | Y | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Sharath Kumar | Palmer Hong, Melissa Eleuteri
| Marketing Transformation | Drift chatbot replacement | AI enabled chatbot for all 3 BUs |  | Adjusted plan | Closure | Discovery |  | 2025-12-01 | 2027-01-01 | Strategic/LTGrowth | All | Marketing | Global | Jeff Bartoletti, Tracy Dearing, Tracy Swartzendruber | N | N | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Kaila Brittain | Lauren Hewlett, Tracy Swartzendruber, Bindu Oleti
| L2C Transformation | Lead-to-Cash Transformation Wave 2.1 | Wing-to-wing transformation of ITO and OTR |  | Adjusted plan | Closure | Post-Launch | 2024-02-01 | 2025-09-01 | 2025-09-01 | Strategic/LTGrowth | All | Commercial | Global | Scott Reese | Y | Y | Enterprise Applications | All | Enterprise ApplicationsAll | Reza Rahman | Jeff Bartoletti, Kelly Thomas & Melissa Eleuteri | Extra Large | Marketo, SFDC, Oracle CPQ, OIC, Boomi, Fusion, D&A
| Marketing & Commercial Reporting | Marketing Analytics & Reporting | Markting dashboards for all 3 BUs |  | Adjusted plan | Closure | Post-Launch |  | 2025-10-01 | 2025-12-25 | Strategic/LTGrowth | All | Marketing | Global | Jeff Bartoletti, Tracy Dearing, Tracy Swartzendruber | Y | Y | Enterprise Applications | Sharath Kumar, Data & Analytics | Enterprise ApplicationsSharath Kumar, Data & Analytics | Sharath Kumar | Lauren Hewlett, Bindu Oleti
| DT Strategic Initiative | QA Automation | QA Automation |  | On Track | Closure | Agile | Ongoing | Ongoing |  | Productivity | All | All | Global | Anil Kumar Karthik | Y | Y | Enterprise Applications | Mahesh Acholkar, Vikas Goli, Hemant Bissa | Enterprise ApplicationsMahesh Acholkar, Vikas Goli, Hemant Bissa | Mahesh Acholkar | Anil Kumar Karthik | Large | AccelQ
| Sabrix Migration | Migrate to OneSource | Move On-Prem to Cloud |  | On Track | Closure | Post-Launch |  | 2026-03-01 |  | MustDo | All | Finance |  | Mark Deyo | Y | N/A | Enterprise Applications | Enterprise Applications | Enterprise ApplicationsEnterprise Applications | Bala Chander
| DevOps | Middleware Enhancements | Middleware Enhancements |  | On Track | Closure | Agile | 2025-01-01 | Ongoing |  | Strategic/LTGrowth | All | DT | Global | Kishore Pasumarty | Y | Y | Enterprise Applications | Kishore Pasumarty | Enterprise ApplicationsKishore Pasumarty | Kishore Pasumarty | Application Teams | Large
| Vernova HQ Initiatives | Customer Connect SaaS Migration | GEV is moving from an on-premise solution to a SaaS solution. Will require UAT testing from SFDC team |  | On Track | Closure | Post-Launch |  | 2026-02-26 | 2026-03-01 | MustDo | All | Commercial |  | Santosh Kudva | N/A | N/A | GEV HQ | Data & Analytics; Enterprise Applications | GEV HQData & Analytics; Enterprise Applications | Emily Schreiner
| PMO Analytics | GridOS Product360 Dashboard - Phase 2 | Phase 2 of the GridOS Product360 dashboard |  | On Track | Closure | Post-Launch |  | 2025-12-25 |  | Strategic/LTGrowth | Grid | Engineering | Global | Prakash Seshadri | Y |  | Data & Analytics | Data & Analytics | Data & AnalyticsData & Analytics
| Customer Strategic Account Analytics | Customer Strategic Account Analytics | Migration of the SynerGE tool to the GEV HQ team |  | On Track | Closure | Post-Launch |  | 2026-02-26 |  | MustDo | All | Commercial |  | Santosh Kudva |  |  | GEV HQ |  | GEV HQ | Charles Norton
| Vernova HQ Initiatives | OneBiller exit | Exit OneBiller and move functionality to Fusion AR/IBS |  | On Track | Closure | Post-Launch |  | 2026-04-01 |  | MustDo | All | Finance |  | Josh White | Y | N/A | Digitization Programs | Digitization Programs | Digitization ProgramsDigitization Programs | Bala Chander | Josh White
| FDL to VDL Migration |  | Migrate off the FDL platform (owned by EY) to the VDL platform (owned by GEV) |  | On Track | Closure | Post-Launch |  |  |  | MustDo | All |  |  | Santosh Kudva | N | N | GEV HQ |  | GEV HQ
| PMO Analytics | Grid Contract Requirement Management Dashboard | Provide the Product team with insight into product commitments, due dates, and penalties |  | On Track | Closure | Post-Launch |  | 2025-08-01 |  | Strategic/LTGrowth | Grid | Engineering | Global | Prakash Seshadri | Y |  | Data & Analytics |  | Data & Analytics | Emily | Vinay Jammu
|  | Customer 360 Kaizen (Oct 2024) | Data work to support the Customer 360 Kaizen and the ongoing support |  |  | Closure | Post-Launch | 2024-10-01 | 2025-07-01 |  | Strategic/LTGrowth |  | Customer Success | Global | Prakash Seshadri | Y |  | Data & Analytics |  | Data & Analytics | Emily | Dave Seward, Melanie Brittingham | Medium | EMR, Tableau
|  | L2C Reporting Modifications | Reporting changes required to sustain existing reports as a result of the L2C transformation |  | On Track | Closure | Post-Launch | 2024-02-01 | 2025-11-01 |  | MustDo | All | DT | Global | Prakash Seshadri | Y |  | Data & Analytics |  | Data & Analytics | Emily | Karthik | Medium | EMR, Tableau
|  | Romania - Fusion ERP | Migrate Romania to Fusion ERP |  | On Track | Closure | Post-Launch |  | 2025-06-25 |  | Strategic/LTGrowth | Grid | Finance | Global | Raman Nagarajan | Y |  | Digitization Programs |  | Digitization Programs | Bala Chander | Karan Bhalla | Large
| Vernova HQ Initiatives | GEV SMO Project | Migration of integrations on TSA to the Vernova platforms |  | On Track | Closure | Post-Launch | 2024-09-01 | 2025-09-01 |  | MustDo | All | DT | Global | Sripati Neti | Y | Y | Enterprise Applications | Kishore Pasumarty | Enterprise ApplicationsKishore Pasumarty | Kishore Pasumarty | Sripati Neti | Large
| Vernova HQ Initiatives | Dive Dashboard Decommissioning | Replacing the monitoring tool for the integrations platform - mandated by GEV |  | On Track | Closure | Post-Launch | 2025-04-01 | 2025-06-01 |  | MustDo | All | DT | Global | Sripati Neti | Y | Y | Enterprise Applications | Kishore Pasumarty | Enterprise ApplicationsKishore Pasumarty | Kishore Pasumarty | Sripati Neti | Medium
| Grid ServiceNow Transformation | Artifactory Redesign | Software build artifact repository for customer sold software - needed for Grid ServiceNow Transformation. |  | Adjusted plan | Cancelled | Discovery |  | 2025-12-01 | 2026-06-01 | MustDo | Grid | Customer Success |  | Vince Padua | Y | Y | Product Tech Solutions & Operations | Product Tech Solutions & Operations | Product Tech Solutions & OperationsProduct Tech Solutions & Operations | TBD | Max Steele
Note on A1: Definition: To show the current status of the project based on current plan Expected Values: G, Y, R
Note on B1: Definition: High level project name to allow for grouping and ease of reporting
Note on C1: Definition: Name recognized by the teams performing the work
Note on D1: Definition: Short summary of the project to explain the purpose and/or deliverables
Note on E1: Defintion: The team of the leader responsible for delivery of the project Expected Values: Data & Analytics; Digitization Programs; Enterprise Applications; Technology Enablement & Transformation
Note on F1: Definition: To reflect where the project is according to the initial plan that was established Expected Values: On Track; Slip; Adjusted plan
Note on G1: Definition: To indicate the current level of activity being executed on the project Expected Values: Active; Hold; Evaluation; Funnel; Closure
Note on J1: Definition: End date based on the initial plan
Note on K1: Definition: End date based on agreed upon adjustments. Expected Values: Expected to be completed for any project with OTD Status = Adjusted Plan
Note on L1: Definition: Value to indicate the type of project being executed Expected Values: MustDo; Strategic/LTGrowth; Productivity
Note on M1: Definition: Used to indicate the business(es) that are benefiting from the project Expected Values: Grid; MFG; PERS; All
Note on N1: Definition: Used to indicate the primary function of the business obtaining value from the project Expected Values: Commercial; Marketing; Customer Success; Finance; Legal; HR; Strategy; Engineering; All
Note on O1: Definition: used to indicate if there is a specific region obtaining value from the project Expected Values: Global; Namerica; EMEA; APAC
Note on P1: Definition: Indicates the Executive sponsor of the project
Note on Q1: Definition: Used to indicate if the resourcing has been planned for the current year budget Expected Values: Y; N
Note on R1: Definition: Indicates if a benefit is being realized in current year by the project
Note on S1: Defintion: The team of the leader responsible for delivery of the project Expected Values: Data & Analytics; Digitization Programs; Enterprise Applications; Technology Enablement & Transformation
Note on T1: Definition: The teams needed for project delivery. If same as column R, leave blank Expected Values: Expected Values: Data & Analytics; Digitization Programs; Enterprise Applications; Technology Enablement & Transformation
Note on U1: Definition: Concatenation of columns R and S to allow for a filterable option for all projects a specific team is involved with and not just leading
Note on V1: Definition: Individual who is responsible for delivery of the project
Note on W1: Definition: Business Functional Owner for the project
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Leveraging existing FTE's
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Leveraging existing FTE's
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Leveraging existing FTE's
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Leveraging existing FTE's
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Leveraging existing FTE's
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Leveraging existing FTE's
Note on C64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lacking platform; Lacking stakeholder buy-in; Lacking funding
Note on C65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Business Requirement Gathering ongoing; Assumption validations ongoing; Blocked due to infrastructure
Note on C66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gathering business requirements; on hold due to infrastructure
Note on D95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Handed over to Santosh’s team
Note on D97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Handed off to Santosh’s team

## Sheet1
DT Team List | Business Functions
Data & AI | Commercial
Enterprise Applications | Marketing
Technology Enablement & Transformation | Customer Success
Product Tech Solutions & Operations | Finance
GEV HQ | Legal
HR
Strategy
Engineering
All